## Task_Table
ID | Name | Duration | Start | Finish | Predecessors
1 | Create Public Interfaces | 90 | 2007-08-24 08:00 | 2007-12-27 17:00
2 | Model layer interface | 10 | 2007-08-24 08:00 | 2007-09-06 17:00
3 | Model interface Test/Documentation | 10 | 2007-09-07 08:00 | 2007-09-20 17:00 | 2
4 | View layer interface | 40 | 2007-09-07 08:00 | 2007-11-01 17:00 | 2
5 | View layer Test/Documentation | 40 | 2007-11-02 08:00 | 2007-12-27 17:00 | 4
6 | IO layer interface | 10 | 2007-09-07 08:00 | 2007-09-20 17:00 | 2
7 | IO layer Test/Documentation | 10 | 2007-09-21 08:00 | 2007-10-04 17:00 | 6
8 | Application layer interface | 10 | 2007-09-21 08:00 | 2007-10-04 17:00 | 6
9 | Application layer Test/Documentation | 10 | 2007-10-05 08:00 | 2007-10-18 17:00 | 8
10 | Componentize Layers/Plugin | 20 | 2007-12-28 08:00 | 2008-01-24 17:00
11 | Refactor manager to handle plugins via OSGi | 20 | 2007-12-28 08:00 | 2008-01-24 17:00 | 1
12 | Add Aspects | 90 | 2008-01-25 08:00 | 2008-05-29 17:00 | 10
13 | Provide aspects for factory methods | 40 | 2008-01-25 08:00 | 2008-03-20 17:00
14 | Provide aspects for OSGi registry | 10 | 2008-03-21 08:00 | 2008-04-03 17:00 | 13
15 | Provide aspects for resource handling | 20 | 2008-04-04 08:00 | 2008-05-01 17:00 | 14
16 | Provide aspects for application and vew layers | 20 | 2008-05-02 08:00 | 2008-05-29 17:00 | 15

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units

## Info_Table
Microsoft Office Project | Template ID: | 9876543210 | (Do Not Edit)
Project is a project management program designed to help you plan and manage your projects and communicate project information.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Project makes it easy to get started and learn as you go.
With this template you can export data to Excel to perform more advanced numerical analysis. Then you can import project data back into Project to perform standard project tasks, such as:
* Seeing your tasks linked in a Gantt Chart
* Seeing how much work each person on the team has assigned to them
You can easily import this information back into Project and keep working without reentering data.